## Template
|  | 1.0 Planning and Development of App Weekly Status meetings |  |  | Level 1 Project level
1.0 Design the App | 2.0 Develop the App |  | 3.0Test App | 4.0 Launch App | Level 2 Phase level
1.1Finalize App requirements | 2.1Initial App Prototype |  | 3.1Intial Beta test | 4.1Hire two new IT personnel | Level 3 Work package level
1.11 IT infrastruture upgrades | 2.11 IT interface Development |  | 3.11Gather feedback from Stakeholders | 4.11 Train personnel on App
1.12 Data Feeds Installation Hardware | 2.1.2 Test App Prototype interface |  | 3.1.2Upgrade App& IT infrastruture | 4.1.2Launch App and gather feeback
1.1.3Test IT infrastruture equipments | 2.1.3 Ask for feedback from IT |  | 3.1.4 Testing App Phase 2 | 4.1.3 Improve app & incoporate feedback
1.1.4 Document Process | 2.1.4 Document Process |  | 3.1.4 Feedback from Stakeholders | 4.1.4 Make adjustments
1.1.5 | 2.1.5 |  | 3.1.5 Document Process | 4.1.5Monitor App effectiveness &plan for Version2