## Risk Register Template
Project: ACME HEALTH INNOVATION C SUITE MARKETING APP PROJECT Date: April 2023
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
| Over Budget | Redced ROI | Affect xceution of Project | Finance Director | O | 5 | -5 | -25 | Project funds | Manage and Control Funds
| Design Flaws | App launch delays | delays in developing software | Marketing Director | T | -2.5 | 5 | 17.5 | designing | Operational lead & SME
| Development Delays | App launch delays | delays in testing of App software | Prduct Owner | T | 4 | 4 | 16 | programming | Productmanagement,feedback from customer
| IT Capability issues | Reduced ROI | App launch delays | IT Lead | IT | 3 | 4 | 12 | Software ,harware uprages | T infrastructure upgrades and security upgrades
| Internal App development Capacity | App launch delays | App launch delays | Project Core team,IT ersonnel | T | 2 | 3 | 6 | marketing data Analytics | Marketing an App testing
| Approval of Software Usage | App testing delays | beta testing and final testing | CEO,Marketing Director | T | 2 | 3 | 6 | Software launch | beta test,final test
Total Risk Score | [7 empty] | 32.5 | Risk Exposure
|  | Probability risk rating |  | Impact risk rating
|  | 5: High |  | 5: High
|  | 4: High to moderate |  | 4: High to moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to low |  | 2: Moderate to low
|  | 1: Low |  | 1: Low